## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time
Group Number |  | 27
Participant 1 |  | Donner Philip
Participant 2 |  | Klemens Hamburger
Participant 3 |  | Muck Martin
Participant 4 |  | Schild Daniel
Participant 5 |  | Yilmaz Tomas
Mentor |  | Redl Chistoph
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Zusammenführen der Komponenten | 8 | 9 | 1
2 | Bugfixes | 4 | 3 | -1
3 | LifePointsHud | 1 | 1 | 0
4 | Hauptmenü implementieren | 1 | 1 | 0
5 | Win/Lose screen erstellen | 3 | 3 | 0
6 | Shooting mergen | 2 | 3 | 1
7 | Bounce mergen | 2 | 2 | 0
8 | Hit registration mergen | 2 | 1 | -1
… |  |  |  | 0
n |  |  |  | 0
8 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol